## Slide 1
Continued IPT of patients to Independent Sector
Reopening of County 7th theatre
Increase in Non-ICF contracts to free up capacity over winter
Patient validation of waiting list – telephone and chatbot
External validators to deep dive 52ww
Extend use of “Luna” validation tool to target validation
Insourcing surgeon & theatre team for high volume low complexity cases
Increased use of advice & guidance to divert patients who don’t need to be referred to secondary care.
Further rollout of PIFU to free up capacity for new outpatient appointments
Contracting resource to scope out potential third party capacity – mutual aid requests
Top 10 High Impact Actions

## Slide 2
Text message successfully sent to ~3k patients on Plastics FUOPA backlog to validate waiting list. Responses to be analysed this week, will inform decision to roll out to other services and patient cohorts e.g. long RTT waiters. Specialised Medicine to send next cohort of messages to long RTT waiters
Awaiting further instruction as to ISP contracting arrangements 22/23, but early indicators suggest to be rolling forward of arrangements for Q3 2021/22 i.e. IPT contract between CCGs and ISPs. Unsure at this stage what this will look like given switch to ICS in July.
CCG and ISP partners have requested information on what capacity is likely to be required over the next financial year – in development
Surgical wards returned to Surgery; increased theatre booking to meet increase in capacity; theatre timetable currently being revised
Other Escalations & Highlights

## Slide 3
Theatre Recovery Programme – Restoration Roadmap (as @19.01.22)
January 2022
February 2022
March 2022
W/C 07.02.22 Reinstate Forward Loading
W/C 31.01.22
County 6th Theatre
W/C 14.02.22 Reinstate TPG & Utilisation
W/C 21.02.22
Cease Prioritisation meeting
W/C 14.02.22
T&O Weekend County sessions start (18wks)
W/C 07.03.22
Reinstate Th11
April 2022
W/C 14.02.22
Reinstate Th 32
W/C 11.04.22
Reinstate Th 28
W/C 11.04.22
Reinstate Th 29
W/C 04.04.22
County 7th Theatre
W/C 11.04.22
Launch Robotic Suite
14 sessions
Saturday -Sunday
10 sessions
Monday – Friday
20 sessions
Monday – Friday
30 sessions
Monday – Friday
W/C 14.03.22
Reinstate Th 12